## Instructions
Instructions | Enter your team name as specified in the cell below. When doing cross-team acceptance testing, enter the name for the testing group. Fill-in the Test Plan worksheet with all the remaining User Stories in your Product Backlog. Since Product acceptance is from the perspective of the end-user, only add User Stories that pertain to the Owner or Buyer and do not include User Stories specifically for the REST API service (e.g. AS a developer...). As your user stories are refined, add the acceptance criteria for each user story. Use a separate worksheet to provide any specific test case data that the tester needs to use. As tests are performed in each sprint, indicate Pass/Fail. Note that there are separate columns for each sprint. The tester should add initials and a date in the comments column. If the test failed, the tester is required to add additional information about the failure. The status cell will color code based on the test results. The comments cell will color code when a test result exists but no information is entered. Save this test plan with a name formatted as "term-swen-261-sec-letter name", e.g. 2231-swen-261-10-a Speedy Racers.xslx. Submit this file per the instructions specified for the sprint submissions and cross-team testing.
Team Name | Your team name as "team-swen-261-sec-letter name", e.g. 2235-swen-261-04-1a-tbd
Testing Team Name | 2235-swen-261-04-2b-2bOrNot2b

## Test Plan
User Story | Acceptance Criterion | Sprint 2 | Tester initials; date; comments (required if test failed) | Sprint 3 | Tester initials; date; comments (required if test failed)
As a helper I want to see a list of needs so that I choose what to contribute to. | Given that I am on the u-fund site when I am not on the Needs page then I must see a means to navigate to the Needs page. | Pass | VR; 2024-03-24; NA | Pass | AC ; 04/03/24 ; ...
| Given that I am not on the Needs page when I choose the Needs page then I am taken to the Needs page. | Pass | VR; 2024-03-24; NA | Pass | AC ; 04/03/24 ; ...
| Given that I am on the Needs page when there are no needs in the cupboard I see a message indicating that that there are no needs available to contribute. | Pass | VR; 2024-04-03; Added since last testing | Pass | AC ; 04/03/24 ; ...
As a helper I want to see a list of needs and be able to add needs to my funding basket so that I can choose which ones to contribute to. | Given that I am on the Needs page when there are needs in the cupboard then I see each need and short description. | Pass | VR; 2024-03-24; NA | Pass | AC ; 04/03/24 ; ...
| Given that I am on the Needs page when there are needs in the cupboard then I see a means to add each need to my funding basket. | Pass | VR; 2024-03-24; NA | Pass | AC ; 04/03/24 ; ...
| Given that I am on the Needs page when there is a need added to my funding basket then I expect to see the need in my funding basket. | Pass | VR; 2024-03-24; We should probably add the ability to type in the quantity of the need you want to fund, and make sure you can’t add more than the specified quantity. | Pass | AC ; 04/03/24 ; ...
As a Helper I want to be able to remove a need from my funding basket so that I can manage what I am planning to fund. | Given that I want to remove a need from my funding basket when I click “remove” then I expect the need to be removed from my funding basket. | Pass | VR; 2024-03-24; We should add a functionality to remove only a certain number of needs, such as if you want to fund 10 books instead of 15. | Pass | AC ; 04/03/24 ; ...
As a Helper I want to be able to check-out and fund all of the needs in my funding basket so that I can contribute to those needs. | Given that I want to contribute to a need when I checking out my funding basket then I expect the need to be removed from my funding basket, and the need quantity in the cupboard to be subtracted from. | Pass | VR; 2024-03-24; We need to remove a need from the cupboard if it is fully funded and quantity is 0, or at least mark it as funded. | Pass | AC ; 04/03/24 ; ...
As a Helper I want to be able to search for a specific need so that I can find causes that match my interests. | Given that I want to search for a specific need in the cupboard when I search for the specific need then I expect the relevant queries to be shown to me. | Pass | VR; 2024-03-24; NA | Pass | AC ; 04/03/24 ; ...
As a U-fund Manager I want to be able to add needs to the cupboard so that Helpers can see what our organization needs. | Given that I enter the information for a need when I want to add a need to the cupboard then I expect the need to be added to the cupboard. | Pass | VR; 2024-03-24; NA | Pass | AC ; 04/03/24 ; ...
As a U-fund Manager I want to be able to edit existing needs in the cupboard so that Helpers can have accurate and relevant information in the cupboard. | Given that I edit the information for the need when I click “Edit” and enter new information then I expect the need to be updated. | Pass | VR; 2024-03-24; NA | Pass | AC ; 04/03/24 ; ...
As a U-fund Manager I want to be able to remove needs from the cupboard so that Helpers can see the updated and relevant cupboard. | Given that I want to remove a need from the cupboard when I click “x” then I expect the need to be removed from the cupboard. | Pass | VR; 2024-03-24; NA | Pass | AC ; 04/03/24 ; ...
As a Helper I want to be able to securely log into and out of my account using a simple username so that I can perform my desired actions | Given that I want to access my account when I sign in with my username then I expect to be logged in and allowed to performed helper functions. | Pass | VR; 2024-03-24; NA | Pass | AC ; 04/03/24 ; ...
| Given that I want to log out of my account when I click “sign out” then I expect to be logged out. | Pass | VR; 2024-03-24; NA | Pass | AC ; 04/03/24 ; ...
As a U-Fund Manager I want to be able to log into my account with the username “admin”. (All other usernames belong to Helper accounts). | Given that the U-Fund Manager wants to log in, then I expect the username to be “admin” and that account should have U-Fund Manager privileges. | Pass | VR; 2024-03-24; NA | Pass | AC ; 04/03/24 ; ...
| Given that I want to log out of my account when I click “sign out” then I expect to be logged out. | Pass | VR; 2024-03-24; NA | Pass | AC ; 04/03/24 ; ...
As a Helper I want to submit suggestions to add a need to the cupboard to the U-fund Manager so that I can contribute to my suggested needs. | Given that I want to suggest a need when I submit my need as a message to the U-Fund Manager then I expect my message to be sent to the U-Fund Manager. | Pass | VR; 2024-04-08; The user can delete messages.
As a Helper I want to be able to sort the needs listed in the cupboard by dollar amount so that I can view the needs in my desired order. | Given a list of needs when I want to view the needs arranged alphabetically or by dollar amount I expect to see a list of needs to be arranged in that order. | Pass | VR; 2024-04-08; N/A
As a U-fund Manager I want to be able to read suggestions from the Helper so that I add the need to the cupboard at my discretion. | Given a I want to view suggestions when at on the home page then I want to see a list of suggestions submitted by Helpers. | Pass | VR; 2024-04-08; The admin has the text box to input a message but obviously cannot send it. It would be better for the admin to not be able to view this at all.